## Slide 1
ENGINEERING DESIGN DEPARTMENT · OPERATING MODEL PROPOSAL
From Reactive Engineering
to Predictable Engineering
Protecting engineering capacity through controlled demand management.
Today: random demand
INTAKE
Single entry point
1
2
3
Committed work packages
Predictable delivery
Executive Briefing · August 2026
Notes: Opening framing: same engineers, same demand — a different operating system for how work enters, gets prioritized, and gets delivered.

## Slide 2
AS-IS · CURRENT STATE
Work reaches engineers from every direction
Simulation 1 — how work happens today
Annual Expansion Plan
Full-year project portfolio
Planned work keeps slipping
ENGINEERING DEPARTMENT
Engineer A
6 task switches today
planned work paused
Engineer B
4 open “urgent” jobs
planned work paused
Engineer C
3 status calls today
planned work paused
Retail
email request
Real Estate
email request
CEO Office
email request
Operations
email request
Security
email request
Facilities
email request
Projects
email request
URGENT — need it today!
No central intake
No filtering
No prioritization
Requests hit engineers directly
Scope changes mid-execution
Resource conflicts
Constant status requests
No delivery dates
PAIN
POINTS
✗ Constant interruptions
✗ No visibility
✗ No workload control
✗ No commitment dates
✗ Low productivity
✗ Context switching
✗ Coordinators, not designers
Engineering Design Delivery System
02
Notes: AS-IS: no intake, no filter, no priority. Seven departments email engineers directly; engineers absorb interruptions and become coordinators.

## Slide 3
TO-BE · FUTURE STATE
One front door — the Engineering Design Delivery System
Simulation 2 — the proposed operating model
ALL REQUESTS
Retail
Real Estate
CEO Office
Operations
Security
Facilities
Projects
Requests keep arriving — 24/7
Annual Engineering Plan
ENGINEERING INTAKE
Single entry point — no engineer receives requests directly
ENGINEERING PIPELINE
REQ
P1
REQ
P2
REQ
P3
REQ
P4
REQ
P5
Every request is logged, scored and visible — nothing gets lost
EACH REQUEST CARRIES
Priority
Business Value
Required Date
Complexity
Estimated Effort
Owner
Status
WEEKLY ENGINEERING PLANNING SESSION
Management + stakeholders decide: Priorities · Scope · Capacity · Delivery commitments
RELEASED: Work Package → Engineering Team
Only after planning is work released — nothing bypasses the gate.
Engineering Design Delivery System
03
Notes: TO-BE: all demand converges on one intake. The pipeline holds and scores everything; the weekly planning session is the only gate that releases work.

## Slide 4
TO-BE · FUTURE STATE
The Engineering Pipeline — every request follows one path
From first email to delivered design
DEMAND INTAKE · 1–3
GOVERNANCE & PLANNING · 4–7
EXECUTION & DELIVERY · 8–10
01
Request Received
Logged at central intake
02
Intake Review
Is it engineering work?
03
Information Validation
Complete brief? Data ready?
04
Engineering Pipeline
Queued & visible to all
05
Prioritization
Priority × business value
06
Capacity Check
Free slots per capability?
07
Work Package Creation
Locked scope for the cycle
08
Engineering Execution
Focused design work
09
QA
Design review & checks
10
Delivery
Committed date met
Stages 1–7 absorb and govern demand. Engineers only ever see stages 8–10 — released, planned, capacity-checked work.
This is an engineering delivery pipeline — inspired by flow principles, designed for engineering design work (not a software process).
Engineering Design Delivery System
04
Notes: Ten stages from request to delivery. The lock on stage 7 is the release gate: work is packaged and locked before engineers ever see it.

## Slide 5
TO-BE · FUTURE STATE
Balancing unlimited demand against fixed capacity
Released by capacity — not by urgency
INCOMING DEMAND
Continuous · unbounded · from every department
27
new engineering requests received this week
REQ-112 · Retail
REQ-113 · Security
REQ-114 · CEO Office
REQ-115 · Facilities
REQ-116 · Operations
REQ-117 · Projects
REQ-118 · Real Estate
REQ-119 · Retail
REQ-120 · Operations
REQ-121 · Facilities
REQ-122 · Security
REQ-123 · Retail
…and more arriving every day
WEEKLY PLANNING SESSION
RELEASE DECISION
Priority × Business Value × Available Capacity
✗ not urgency ✗ not who shouts loudest
Demand exceeds capacity every week —
planning decides what wins, openly.
ENGINEERING CAPACITY
Fixed weekly slots per engineering capability
Cost Estimation
3 / wk
Architectural Design
2 / wk
Site Evaluation
2 / wk
Space Planning
2 / wk
BOQ Preparation
3 / wk
Design Review
4 / wk
Total capacity: 16 project slots / week
Example: Cost Estimation can complete 3 projects this week → only 3 are released. Everything else waits safely in the pipeline.
Engineering Design Delivery System
05
Notes: The core management message: demand is unlimited, capacity is fixed and known per capability. Work is released by capacity — never by urgency.

## Slide 6
TO-BE · FUTURE STATE
A released Work Package is a commitment
Locked scope · protected team · committed date
WEEK 1 PLANNING
Pipeline reviewed
Capacity checked
Package approved
WORK PACKAGE A
Project 1 — Architectural Design
Project 2 — Cost Estimation
Project 3 — Site Evaluation
Scope locked at release — no additions mid-cycle
ENGINEERING TEAM
Works only on
Package A during
the agreed cycle
COMMITTED DELIVERY
End of Week 4 — a date stakeholders can trust
New urgent request arrives mid-cycle
EXCEPTION
GOVERNANCE
approved → enters the package
declined → waits in the pipeline
THE PACKAGE MOVES AS ONE STABLE UNIT
WEEK 1
WEEK 2
WEEK 3
WEEK 4
DELIVERY
Package A — stable scope from release to delivery
No new work enters a released package without governance approval — that is how delivery dates become predictable.
Engineering Design Delivery System
06
Notes: The package is the unit of commitment. Mid-cycle requests hit the exception-governance diamond, not the engineers. Stability = predictable dates.

## Slide 7
TO-BE · FUTURE STATE
The engineering work cycle — focus protected for four weeks
Swimlane — one full cycle
INCOMING REQUESTS — CONTINUOUS
ENGINEERING PIPELINE — requests wait here for the next planning session
INTERRUPTION BARRIER — nothing crosses mid-cycle
ENGINEERING TEAM — PROTECTED
WEEK 1
PLANNING
WEEK 2
ENGINEERING DESIGN
WEEK 3
ENGINEERING DESIGN
WEEK 4
QA
DELIVERY
PACKAGE
✓ Engineers stay focused — zero interruptions inside the cycle
next cycle begins — the pipeline feeds Week 1 planning
Demand never stops — but it never touches an engineer mid-cycle.
Engineering Design Delivery System
07
Notes: Swimlane: requests keep arriving in the top lane but are absorbed by the pipeline. The barrier protects the 4-week cycle: Planning, Design, Design, QA, Delivery.

## Slide 8
AS-IS vs TO-BE
The difference at a glance
Built to be understood in 30 seconds
TODAY — REACTIVE
Random arrows everywhere
Constant interruptions
Emails from all directions
Broken workflow
Direction changes daily
No commitment dates
TOMORROW — PREDICTABLE
INTAKE
PIPELINE
PLANNING
PACKAGE
DELIVERY
One straight line from request to delivery
One single flow
Controlled queue
Stable work packages
Central governance
Clear priorities
Predictable delivery
The same demand — run through a different system.
Engineering Design Delivery System
08
Notes: The 30-second slide: identical demand on both sides. Left, it lands on people; right, it flows through a system.

## Slide 9
MANAGEMENT BENEFITS
What management gains
12 dimensions, one decision
DIMENSION | CURRENT STATE — REACTIVE | FUTURE STATE — PREDICTABLE
Request Intake | ✗ Email to any engineer, any time | ✓ Single central intake — one front door
Prioritization | ✗ First come / loudest voice wins | ✓ Scored by priority, value and capacity
Visibility | ✗ Work hides in personal inboxes | ✓ Full pipeline visible to management
Capacity Planning | ✗ Unknown — always overloaded | ✓ Fixed weekly slots per capability
Engineer Focus | ✗ Interrupted daily, constant switching | ✓ Protected inside the work package
Delivery Predictability | ✗ Dates slip continuously | ✓ Committed date per work package
Governance | ✗ Ad-hoc decisions, no gate | ✓ Weekly planning + exception process
Customer Expectations | ✗ Everything “urgent”, nothing certain | ✓ Clear commitments and queue position
Resource Utilization | ✗ Fragmented by context switching | ✓ Full slots spent on planned work
Quality | ✗ Rushed under pressure | ✓ Dedicated QA week in every cycle
Management Reporting | ✗ Manual chasing for status | ✓ Pipeline and package status on demand
Workload Balancing | ✗ Random — whoever gets asked | ✓ Matched to capability capacity
Same engineers. Same demand. A different operating system for work.
Engineering Design Delivery System
09
Notes: Twelve dimensions of improvement — each row is a management capability the department gains without hiring a single additional engineer.

## Slide 10
THE TRANSFORMATION
From Reactive Engineering to Predictable Engineering.
Protecting engineering capacity through controlled demand management.
01
SINGLE INTAKE
Every request enters through one front door. Engineers are never interrupted directly — the system absorbs the demand.
02
CAPACITY-BASED RELEASE
Work is released weekly against real capability capacity — priority and business value decide, not urgency.
03
COMMITTED WORK PACKAGES
Locked scope per cycle turns engineering effort into delivery dates stakeholders can trust.
The decision requested: approve the Engineering Design Delivery System — stand up Central Intake and the Weekly Planning Session.
Prepared for Executive Management · August 2026
Notes: Close on the decision: approve the operating model, stand up intake and weekly planning. No new headcount — a new system for the same team.